## Sheet1
Task No. | Task | Time taken | Date (Starting 05-Aug-19) | Dependencies
1 | Setting up development environment. | 1 week | 2019-08-12
2 | Creating temporary UI and researching react-native. | 2 weeks | 2019-08-26 | 1
3 | Integrating project with iOS Spotify SDK. | 8 weeks | 2019-10-21 | 2
4 | Designing and implementing a responsive and functional UI for beginning of user-story. | 2 weeks | 2019-11-04 | 1
5 | Implementing the ability for users to create and terminate a lobby. | 1 week | 2019-11-11 | 4
6 | Implement the ability to join/leave a lobby and vote for their preferred song. | 1 week | 2019-11-18 | 2,4
7 | Implement the switching of songs to the most voted. | 0.5 weeks | 2019-11-18 | 6
8 | Write up the progress report. | 0.5 weeks | 2019-11-25
9 | Implement thumbs-up/thumbs-down on current song. | 1 week | 2019-12-01 | 6
10 | Implement a vote-weighting system. | 1.5 weeks | 2019-12-11 | 9
11 | Integrate with Genius API (for displayable lyrics) | 2.5 weeks (Factoring in Christmas holidays) | 2019-12-28 | 4
12 | Implement the displayable lyrics during songs. | 2 weeks | 2020-01-11 | 11
13 | Researching neural networks. | 1 week | 2020-01-18
14 | Designing the neural network. | 1 week | 2020-01-25 | 13
15 | Implementing the neural network recommendation system. | 2.5 weeks | 2020-02-14 | 14
16 | Implementing the chat room. | 0.5 weeks | 2020-02-17 | 4
17 | Creating and running the test suite. | 1 week | 2020-02-24
18 | Preparing the oral presentation. | 1 week | 2020-03-02 | 17
19 | Majority of final report. | 7 weeks | 2020-04-20 | 17
20 | Finishing touches on final report. | 1 week | 2020-04-27 | 19