## Sheet1
When | Event | col_size
2019-07-01 |  | 0 | Task No. | Task | Time taken (weeks) | Date (starting 05-Aug-19) | Dependencies (Task No.)
2019-08-05 | Initial commit | 1 | 1 | Setting up the development environment | 1 | 2019-08-12
2019-08-09 | Preliminary UI developed | -1 | 2 | Developing the preliminary UI and researching react-native | 2 | 2019-08-26 | 1
2019-09-19 | Native Bridging Module developed | 1 | 3 | Developing and integrating the Native Bridging Module | 8 | 2019-10-21
2019-10-09 | Specification submitted | -1 | 4 | Developing basic REST endpoints locally | 5 | 2019-11-25 | 3
2019-11-19 | Implemented and integrated basic REST endpoints locally | 1 | 5 | Researching AWS and developing DynamoDB Database | 4 | 2019-12-23 | 4
2019-11-25 | Progress Report submitted | -1 | 6 | Deploying WebSocket API and most of REST API on AWS | 4 | 2020-01-26 | 4, 5
2019-12-27 | Development of the database | 1 | 7 | Researching machine-learning and training models | 4 | 2020-02-23
2019-12-29 | Began development of WS API and migration of REST API | -1 | 8 | Deployed machine-learning models and integrated with REST API | 0.5 | 2020-02-26 | 7
2020-01-25 | REST & WS API deployed on AWS |  | 9 | Final UI partially implemented for oral presentation | 0.5 | 2020-03-02 | 2
2020-02-20 | Artist & Genre inference models trained | -1 | 10 | Final UI fully implemented | 1 | 2020-03-09 | 2
2020-02-25 | Recommendation system deployed & integrated | 1
2020-03-01 | Final UI partially implemented for presentation | -1
2020-03-02 | Presentation | 2
2020-04-01 | Final UI implemented | -1
2020-04-10 | Began Testing | 1
2020-04-30 |  | 0
]